## Sheet1
Risk | Resolution Measures | Justification
Timeline Issues | Factor in holidays, Plan for sick days, Prepare for lost workers, Expect Emergency delays, Delays in Approvals, Time for testing. | Plan for the worst and aim for the best
Budget Issues | Get input from experts for quotes as needed, Add security padding to quote for added protection, Action plans to handle costs of change controls, delays, and other project changes. | Ensure scope is clearly defined in order to determine an accurate budget.
Organizational Issues | Balance needs of dev team and expectations of customer, Choose team members with skills that are a good match for the project. | Plan for efficient execution of the project.
Performance Issues | Consider benchmark and threshold testing throughout the project so that goals are moving in the right direction. | Ensure that user and partner expectations on performance are in the plan.
Requirements Change | Plan for change during prototyping, discovery, and integration, Expect routine changes during the project to impact the functional requirements. | Poorly-planned project can lead to critical failures.
Iteration 1, 4 weeks
August 27, 2018 - September 21, 2018
Iteration 2, 4 weeks
September 24, 2018 - October 19, 2018
Iteration 3, 4 weeks
October 19, 2018 - November 16, 2018
UC04: Login
Points: 3
Priority: 1
Dependencies: None
UC05: Logout
Points: 3
Priority: 1
Dependencies: UC04
UC01: Search for Programs
Points: 5
Priority: 3
Dependencies: UC04, UC05
UC02: Display Program Details
Points: 5
Priority: 2
Dependencies: UC01, UC04, UC05
UC03: Submit Online Application
Points: 3
Priority: 2
Dependencies: UC01, UC04,
UC05
UC06: Edit Online Application
Points: 5
Priority: 2
Dependencies: UC03, UC04,
UC05
UC07: Check Application Status
Points: 5
Priority: 5
Dependencies: UC03, UC04,
UC05, UC06
UC08: Submit Recommendation
Points: 3
Priority: 5
Dependencies: None
UC09: Approve Course Equivalency Form
Points: 3
Priority: 4
Dependencies: UC04, UC05